Work plan

Deadlines

2016-02-29 Choose a project proposal and send the result via email to epsatisep@gmail.com

2016-03-08 Define the Tasks (what must be done - all members must participate in all tasks), subtask allocation (who does what) and Gantt chart (when) of the project and insert them on the wiki (planning)

2016-03-14 Upload the “black box” System Diagrams & Structural Drafts to the wiki

2016-03-29 Upload the detailed System Schematics & Structural Drawings to the wiki and finish the cardboard scale model of the structure

2016-04-04 Upload the List of Materials (what & quantity) to the wiki

2016-04-11 Complete the List of Materials (local providers & price - including VAT and transportation) to the wiki

2016-04-16 Upload the Interim Report and Presentation to the wiki. The report must contain the Introduction, including the tasks, team members allocation and Gantt chart, State of the Art, Marketing Plan, Project Management, Eco-eficiency Measures for Sustainability, Ethical and Deontological Concerns, Proposed Solution and Bibliography chapters

2016-04-21 Interim Presentation, Discussion and Peer, Teacher and Supervisor Feedbacks

2016-04-29 Upload refined Interim Report (based on Teacher & Supervisor Feedbacks)

2016-05-30 Upload the Functional Tests' Results to the wiki

2016-06-11 Upload the Final Report, Presentation, Video, Paper, Poster and Manual

2016-06-16 Final Presentation, Individual Discussion and Assessment

2016-06-21:

Update the wiki with all correction suggestions

Hand in a CD with the corrected deliverables (source + PDF) together with all code produced to the EPS coordinator

Hand in one printed exemplar of the corrected report to the EPS coordinator

2016-06-23:

Hand in the prototype and user manual to the client

Receive the EPS@ISEP certificate

Tasks

Task	Responsible
Planning
Find the tasks	All
Create the Gantt	All
System Diagrams & Structural Drafts	Alvaro
System Schematics & Structural Drawings	Alvaro
Research
Physical Characteristics Fish	Martin, Alvaro
Programming Research	Achim
Targets	All
Design	Terry, Alvaro
Engineering Development	Terry, Martin
State of the Art	All
Marketing Study
Compare suppliers	Justyna
Compare budget and the project	Justyna
Modifications	All
Materials
What	Achim, Terry
Quantity	Achim, Terry
Prototyping
Materials	All
Design	Terry, Alvaro
Construction	All
Functional Tests	All
Improvement/modification	All
Report/Presentation
Upload Final Report, Presentation, Video, Paper, Poster, Manual and Website	All
Final Presentation, Individual Discussion and Assessment	All
Wiki
Update the wiki with all correction suggestions	All
Hand in a CD with the corrected deliverables together with all code produced to the EPS coordinator	All
Hand in one printed exemplar of the corrected report to the EPS coordinator	All
Final Submission
Hand in the prototype and user manual	All
Certificate	All

Gantt Chart

System Diagram

Electronic Schematic